## GANTT
Name of the project: | visEUalisation
PROJECT TIMETABLE
| 2018 | XI | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII | I | II | III | IV | V | VI | VII | VIII | IX | X | XI | XII
| MONTHS | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
Project activity*
A1 (Project management) | bar: M1 to VII M26
A2 (Dissemination Plan) | bar: M1 to VII M26
A3 (Project Quality Plan) | bar: M1 to VII M26
M1 (Kick off Poland) | bar: M2 to M4
O1/A1 | bar: M1 to M4
O1/A2 | bar: M1 to M3
O1/A3 | bar: M2 to M4
O1/A4 | bar: M3 to III M17
C1 (TechLab - Spain) | bar: M5 to M7
O1/A5 | bar: M5 to M7
O1/A6 | bar: M6 to IX M11
O1/A7 | bar: M6 to IX M11
C2 (CreativeLab - Austria) | bar: M10 to X M12
O1/A8 | bar: M5 to VII M22
O1/A9 | bar: III M17 to VII M22
O2/A1 | bar: IX M11 to XI M13
O2/A2 | bar: M5 to XII M14
M2 (Germany) | bar: XI M13 to I M15
O2/A3 | bar: M5 to II M16
O2/A4 | bar: XI M13 to IV M18
M3 (Austria) | bar: IV M18 to VI M20
O2/A5 | bar: I M15 to V M19
O2/A6 | bar: IV M18 to VII M24
O2/A7 | bar: V M19 to VII M24
M4 (Poland) | bar: VII M26
O2/A8 | bar: VII M23 to VII M25
E1 (Poland) | bar: VII M24 to VII M25
E2 (Germany) | bar: VII M24 to VII M25
E3 (Austria) | bar: VII M24 to VII M25
E4 (Spain) | bar: VII M24 to VII M25
Please insert rows as needed
*Project activity types:
| An | M1: - PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
| On/An | M1: - INTELLECTUAL OUTPUTS/ACTIVITIES
| Mn | M1: - TRANSNATIONAL PROJECT MEETINGS
| En | M1: - MULTIPLIER EVENTS
| Cn | M1: - LEARNING/TEACHING/TRAINING ACTIVITIES
| n | M1: - number of the activity
Please enter all main project activities and meetings, intellectual outputs and related activities, multiplier events and training/teaching/learning activities. Use the reference numbers as they appear in the application form. Where no numbers exist in the application form (i.e. for activities included in project management and implementation), use reference numbers A1, A2 etc. For each activity, meeting or event, indicate the month(s) in which they will be produced/take place by colouring the corresponding cells.

## descr
O1
Activities:
O1/A1 Research on the latest development on the importance of the visual and auditive senses for education with a special focus on the benefit for the learner. Development of educational and pedagogical framework / benefits of visualisation techniques in adult education including creativity and innovation techniques. (ALP/2Kroner)
O1/A2 Analysis of the Open Source Software (updating the State of Art). Explaining the pros and cons of each one. (AIJU)
O1/A3 Deciding on the topics & methods for each topic and defining the visEUalisation eLearning Platform (Free and Open Source). (all partners)
O1/A4 Adapting templates and creating online tutorials (Technical aspects and how to create visual content). (all partners)
O1/A5 Developing video scribing describing the visEUalisation eLearningPlatform (AIJU)
O1/A6 Development of theoretical content Creativity Techniques for Visual Thinking (ALP/ 2Kroner)
O1/A7 Development of theoretical content Storytelling Methodologies (ALP / 2Kroner)
O1/A8 Developing eLearning platform. (AIJU)
O1/A9 Testing and eLearning platform refinement. (all partners)
O2
Activities:
O2/A1 Collecting Open Resources (graphic resources, music and sounds) (AIJU)
O2/A2 Redefining topics & develop a clear structure for the topcis (5 topics per partnerorganisation) (all partners)
O2/A3 Developing a Visual Library for each topic. (all partners)
O2/A4 Generating the template for each topic using the Library created. (AIJU)
O2/A5 Implementation of each topic: Developing one video scribing per topic (all partners)
O2/A6 Developing video scribing describing the visEUalisation Database. (AIJU)
O2/A7 Developing a MOOC (Massive online open Courses) (all partners)
O2/A8 Learning Assessment (all partners)